## Project Management Plan
Yearly | Build application for predicting house price in US. Application will be available in web and mobile version.
Week | Task | Diificulty 1-3 1 easy - 3 difficult | Quarter 2 | Quarter 3 | Quarter 4
2022-05-22 | Management planning | 2
2022-05-29 | Assign tasks | 2
2022-06-05 | Demo the planning | 1
2022-06-12 | Research the data | 3
2022-06-19 | Present the data (demo) | 2
2022-06-26 | Get feedback | 2
2022-07-03 | Design the machine learning model | 3
2022-07-10 | Implement the machine learning model | 2
2022-07-17 | Demo the ML model | 1
2022-07-24 | Get feedback | 2
2022-07-31 | Refine the ML model | 2
2022-08-07 | Demo the ML model | 1
2022-08-14 | Get feedback | 2
2022-08-21 | Implement Flask Api | 2
2022-08-28 | Demo the web application | 3
2022-09-04 | Get feedback | 2
2022-09-11 | Refine the web application | 1
2022-09-18 | Demo the web application | 1
2022-09-25 | Get feedback | 2
2022-10-02 | Refine the web application | 2
2022-10-09 | Demo and Launch WebApp Version 1 | 3
2022-10-16 | Get feedback | 2
2022-10-23 | Implement mobile application | 2
2022-10-30 | Demo mobile application | 1
2022-11-06 | Get feedback | 2
2022-11-13 | Add additional feature to machine learning model | 2
2022-11-20 | Implement web and mobile application | 2
2022-11-27 | Demo and Launch Web & Mobile Application v.1.1 | 3
2022-12-04 | Get feedback | 2
2022-12-11 | Plan for year 2 | 2
2022-12-18 | Merry Christmas everyone. (Pay the bonus) | 1
| Goals | Initial planning | Machine Learning model is built | WebApp v.1 is built | Mobile App V.1 is built | Get feedback and fix bugs (v.1.1) | Contemplate on the results, plan for the new year
Formulas:
Week = [Week, row above]+7