## Sheet1
Week | CI | CD | Documentation
2022-10-03 | plan system | plan system | plan documentation
2022-10-10 | create documentation | create documentation | create documentation
2022-10-17 | Clone and build app in Azure | Load test using Locust | create project estimate
2022-10-25 | run test on Azure | Deploy app using Azure pipelines into App services
2022-10-31 | use GitHub Actions to test and lint | Use Azure CLI to deploy and manage an app
2022-11-07 |  | Test application inside of Azure pipelines
2022-11-14 |  |  | Create a portfolio demo
2022-11-21
2022-11-28
2022-12-05
2022-12-12
2022-12-19
| Goals | Goals | Goals
| The project is cloned to Azure Cloud Shell (screenshot) | App and test is loaded using Locust (screenshot) | Readme file with links to Trello board and XLS spreadsheet
| Run test in Azure (screenshot) | App is deployed into Azure App Services using Azure Pipelines | Trello board with key tasks, ToDo, In Progress, Done
| Test and Lint project using GitHub Actions (screenshot) | Azure CLI used to deploy and manage app
|  | App is tested insisde of Azure Pipelines (screenshot) | Youtube screencast covering the following:
Working with Azure Cloud Shell for CI
Working GitHub Actions build
Deployment of CD on the Azure
Machine Learning prediction